Free resource

Club event planning checklist

A timeline for a club event that starts three months out and ends with the thank yous, so nothing is left to the last week.

Three months before

☐  Set the date, checked against holidays and other local events.

☐  Agree the budget and the ticket price. The event budget and ticket tracker finds the break even price.

☐  Book the venue, and get the booking in writing with the deposit and cancellation terms.

☐  Check the club's insurance covers the event, and ask the venue what cover it needs from you.

☐  Name one person in charge, and who decides on spending.

Six weeks before

☐  Book catering, entertainment and hired equipment.

☐  Ask local businesses to sponsor. The sponsorship letter is ready to send.

☐  Open ticket sales or sign ups, and tell members.

☐  Check whether a raffle, alcohol or food sales need a permit where you are.

☐  Make the shift list. The volunteer roster counts who is still needed.

Two weeks before

☐  Confirm numbers with the caterer and the venue.

☐  Email the members who have not booked yet.

☐  Print signs, name badges and the running order.

☐  Arrange a float for any cash sales, counted and signed for.

The week of the event

☐  Remind every volunteer of their shift, the time and where to go.

☐  Print the guest list, with who has paid.

☐  Pack the kit box: tape, scissors, pens, extension lead, first aid kit, card reader, change.

On the day

☐  Arrive early with the key holder.

☐  Check people in against the list, and take payment from anyone who has not paid.

☐  Count the cash with two people, write the total down and both sign it.

☐  Photograph the event, with permission, for the newsletter and the sponsors.

The week after

☐  Bank the takings within two working days.

☐  Pay the bills and the volunteers' expenses.

☐  Thank volunteers, sponsors and the venue.

☐  Type the actual costs into the budget, and write three lines on what to change next time.

Made by renuzy, dues done easy. Looking after dues for a club? See how renuzy can help at renuzy.com. https://renuzy.com/resources/event-planning-checklist